Creative Industries: Creative Project

King’s Park Events Company

Pupil Assessment Booklet 2026–27

| Pupil name |  |
| --- | --- |
| Class |  |
| Events team |  |
| Teacher |  |

Keep this booklet safe and bring it to every lesson.

INSIDE COVER

# About this qualification

Successful completion of this booklet’s formal assessment project contributes to the following awards:

- the J17Y 75 Creative Industries: Creative Project National 5 unit;

- 6 SCQF credit points at SCQF level 5;

- the complete Core Skill Working with Others at SCQF level 5.

## What you need to show

Outcome 1 — Plan the project I contribute ideas, identify tasks and resources, agree responsibilities and help set deadlines.

Outcome 2 — Deliver the project I complete my agreed tasks, use resources safely, review progress and support my team.

Outcome 3 — Evaluate the project I explain what worked, what could improve and what should be done differently next time.

Important The Autumn Music Experience is supported practice. The Christmas Community Celebration is the formal assessment project for J17Y 75.

Adapted for internal educational use from J17Y 75/NAB001, Creative Industries: Creative Project (National 5).

GETTING STARTED

# Welcome to King’s Park Events Company

You will work as part of a real creative events company inside the school. The class works as one company, with smaller teams responsible for different parts of each event. Every pupil must make a clear individual contribution.

## Why are we doing this?

The projects help you develop skills that are useful in school, work and everyday life:

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | creativity | ☐ | problem solving |
| ☐ | teamwork | ☐ | confidence |
| ☐ | communication | ☐ | safe working |
| ☐ | planning | ☐ | evaluation skills |
| ☐ | organisation |  |  |

## What will happen this year?

| Project | Purpose | Assessment status |
| --- | --- | --- |
| Autumn Music Experience | Learn and practise the full event process | Practice evidence |
| Christmas Community Celebration | Plan, deliver and evaluate a community event | Qualifications Scotland assessment evidence |

## How to use this booklet

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Keep it safe. | ☐ | Bring it to every lesson. |
| ☐ | Complete tasks during lessons. | ☐ | Ask for help when needed. |
| ☐ | Record your own contribution. | ☐ | Catch up after absence. |

## Overall success measures

- Both events should be creative and original;

- Both events should be enjoyable for the audience;

- Both events should be organised so that everyone contributes.

WORKING TOGETHER

# Events-company expectations

| Team expectations • Listen to other people. • Share ideas respectfully. • Complete agreed tasks. • Meet deadlines. • Tell the team early if there is a problem. • Help others when appropriate. • Keep materials and spaces safe and tidy. | Meeting rules • Agree an aim for the meeting. • Allow everyone to speak. • Record decisions. • Allocate tasks clearly. • Set deadlines. • Confirm the next review date. |
| --- | --- |

## Health and safety

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Follow staff instructions. | ☐ | Check food hygiene, allergens and dietary needs. |
| ☐ | Use instruments and equipment safely. | ☐ | Plan for accessibility and safe movement. |
| ☐ | Keep cables, routes and emergency exits clear. | ☐ | Behave appropriately with visitors and younger pupils. |
| ☐ | Lift and set up rooms safely. | ☐ | Photograph or record only with staff approval. |

## Working with other departments

Collaboration is encouraged where it helps the event. Possible partners include Music, Drama, Music Technology, Home Economics, Art and Design, Dance/PE and Primary staff.

External communication Contact with primary schools, care homes and community organisations must be handled or approved by staff.

QUICK REFERENCE

# Key vocabulary

| Term | Meaning |
| --- | --- |
| Brief | The instructions that explain what a client needs the team to create. |
| Client | The person or organisation asking for the project. |
| Target audience | The people the event is designed for. |
| Project | A planned piece of work completed to meet a clear aim. |
| Event | A planned experience delivered for an audience at a set time and place. |
| Role | The position or main job a person has in the team. |
| Responsibility | A task or area a person is trusted to complete. |
| Resource | Anything needed to complete a task, including people, time and materials. |
| Equipment | Tools or devices used to complete practical work. |
| Technique | A method or way of using a skill to complete a task. |
| Deadline | The final date or time by which a task must be finished. |
| Review date | An agreed point when the team checks progress and updates the plan. |
| Implementation | Putting the agreed project plan into action. |
| Evaluation | Judging what worked, what did not and how to improve. |
| Running order | The timed sequence of everything that happens during an event. |
| Front of house | The team that welcomes, directs and supports guests. |
| Hospitality | Food, drink and care provided to make guests feel welcome. |
| Technical plan | A record of sound, lighting, playback and equipment needs. |
| Accessibility | Making sure people with different needs can take part safely and comfortably. |
| Health and safety | Actions that reduce risk and protect everyone involved. |
| Contingency plan | A backup plan used if something unexpected happens. |

CHOOSE WHERE YOU CAN CONTRIBUTE

# Possible roles

Teams should contain around four or five pupils. You choose your own team, and every pupil needs a clear individual role. You may combine roles, keep the same role in both projects and specialise in an area that suits your confidence and strengths.

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Event Manager / Project Coordinator | ☐ | Creative Designer |
| ☐ | Assistant Event Manager | ☐ | Room and Decoration Coordinator |
| ☐ | Performer | ☐ | Marketing and Invitations |
| ☐ | Performance Coordinator | ☐ | Front of House |
| ☐ | Workshop Leader | ☐ | Hospitality Coordinator |
| ☐ | Activity Coordinator | ☐ | Guest Experience Coordinator |
| ☐ | Host / Presenter | ☐ | Accessibility and Safety Coordinator |
| ☐ | Sound Technician | ☐ | Photographer / Evidence Coordinator |
| ☐ | Music Technology Coordinator | ☐ | Administrator / Timekeeper |
| ☐ | Equipment Coordinator | ☐ | Running Order Coordinator |

Roles I would feel confident trying

Skills or strengths I could bring to a team

PROJECT 1

Autumn Music Experience

Practice Project

This project helps you learn how to plan, deliver and evaluate an event. You will use what you learn when completing your formal Christmas assessment project.

PROJECT 1 | PRACTICE PROJECT

# Autumn Music Experience brief

## Client

King’s Park Events Company — A fictional creative events company based within King’s Park Secondary School.

## Target audience

- P6 and P7 pupils;

- one primary class;

- a maximum of approximately 20 pupils;

- no previous musical experience is required.

## Background

King’s Park Events Company has been asked to create an engaging music experience for younger pupils. The aim is to introduce them to music, creativity, performance and the opportunities available at King’s Park.

Primary pupils should experience a live performance and take part in creative workshops led by King’s Park pupils.

## Requirements

The class works as one events company. Smaller teams of around four or five pupils each must:

- create a performance;

- create a ten-minute interactive workshop;

- prepare the required resources;

- help deliver the event;

- contribute to a shared opening and/or finale.

Event format The whole event should last approximately 60–75 minutes. Use a rotation system so the primary pupils move between team workshops.

Pupils may specialise in performing, presenting, workshop leadership, technical production, resources or organisation. Not every pupil must perform in the same way, but everyone must contribute.

PROJECT 1 | PRACTICE PROJECT

# Autumn brief: constraints and success

## Considerations and constraints

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | The event is intended to take place at King’s Park. | ☐ | There is no set project budget. |
| ☐ | The exact room and date are TBC. | ☐ | Use instruments and equipment only with staff approval and supervision. |
| ☐ | Staff organise external communication. | ☐ | Make activities accessible to pupils with no previous musical experience. |
| ☐ | Transport planning is not a pupil responsibility. | ☐ | Collaboration with Music, Drama, Music Technology and Primary staff is encouraged. |
| ☐ | Use existing school resources. |  |  |

## Client expectations

The event should:

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | be creative and original; | ☐ | include a clear contribution from every S4 pupil; |
| ☐ | be enjoyable for the primary pupils; | ☐ | be safe and manageable; |
| ☐ | allow the audience to participate; | ☐ | help primary pupils feel confident about visiting King’s Park. |

## Deadline

Term 1 The event will be delivered by the end of Term 1. The exact date will be confirmed by staff.

## Brief check

In one sentence, what is the class being asked to create?

What must every team contribute?

PROJECT 1 | STARTING POINTS

# Autumn ideas bank: performance

Use this bank These are starting points, not fixed choices. Your team may combine ideas or develop something different.

| Live music • band performance • solo performance • vocal group • choir • instrumental ensemble • keyboard performance • guitar or bass performance • percussion performance • tuned-percussion performance • song medley • film-music performance • video-game music • popular-song arrangement • musical theatre performance • acoustic performance | Rhythm and sound • body percussion • drum-circle performance • beatboxing • junk percussion • rhythmic call and response • layered rhythm performance • soundscape • Foley and sound effects • live soundtrack |
| --- | --- |

| Technology • live loop performance • beat making • DJ-style set • electronic music performance • live remix • music-production demonstration • recorded sounds combined with live music | Drama, dance and storytelling • musical story • drama scene with music • dance performance • movement and rhythm piece • spoken-word performance • rap • staged song • audience-participation performance • musical game show • guess-the-song performance |
| --- | --- |

PROJECT 1 | STARTING POINTS

# Autumn ideas bank: workshops

Remember A workshop must be interactive, manageable in ten minutes and accessible to pupils with no previous musical experience.

| Rhythm • body-percussion patterns • copy-the-rhythm games • create a class rhythm • drum circle • percussion ensemble • rhythm relay • rhythm cards • conducting a rhythm group • junk-percussion composition | Singing and voice • teach a chorus • call-and-response singing • vocal warm-ups • singing game • create a vocal soundscape • beatboxing basics • simple harmony • lyric-writing activity • create a short class song |
| --- | --- |

| Instruments • instrument demonstration • keyboard basics • tuned-percussion melody • guitar or bass introduction • percussion exploration • create a small ensemble • learn a simple riff • instrument-family challenge • musical question-and-answer activity | Music technology • create a beat • use loops • record voices • create sound effects • create a short soundtrack • Foley workshop • remix activity • create a jingle • make a soundscape • layer recorded sounds |
| --- | --- |

| Composition and creativity • compose a short piece • create music for a picture • create music for a story • create music for a film clip • build a class soundscape • create a theme tune • invent a school anthem • create a musical character • compose using limited notes • create music from everyday objects | Movement, drama and performance • dance choreography • music-and-movement game • musical storytelling • performance-confidence activity • acting through song • musical theatre activity • freeze-frame and sound • create a short staged performance |
| --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Understanding the brief and audience

## Your task

Read the brief and explain what your team must create for the P6/P7 audience.

## Why are you doing this?

A clear understanding of the brief helps your team choose ideas that are safe, enjoyable and realistic.

## Steps

- Identify the required event parts.

- Think about what younger pupils need.

- Record your answers in your own words.

## Evidence to keep

Your completed brief and audience notes become part of your practice folio.

What must our class deliver?

What must our team create?

What might help P6/P7 pupils feel confident and included?

What could make an activity difficult for a musical beginner?

## Success check

|  | Check |
| --- | --- |
| ☐ | I have identified the audience. |
| ☐ | I have identified the required performance and workshop. |
| ☐ | I have considered accessibility. |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# My first ideas

## Your task

Develop at least one performance idea and one workshop idea before the team decides.

## Why are you doing this?

Individual ideas give the team more creative choices and help everyone contribute to planning.

## Evidence to keep

Your own ideas show your personal contribution to the planning discussion.

Practice model: Rhythm Makers • Performance: a short body-percussion performance. • Workshop: teach three rhythm patterns, then combine them into a group performance.

My performance idea

My ten-minute workshop idea

How the primary pupils would take part

Why these ideas suit the audience

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Our team and chosen ideas

## Our team members

| Name | Strength or interest | Possible role |
| --- | --- | --- |

## Our chosen performance

What will the audience see and hear?

Why did the team choose this idea?

## Our chosen ten-minute workshop

What will the primary pupils learn or create?

What will they achieve by the end?

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Participation and shared moments

## How the primary pupils will participate

What will pupils do rather than only watch?

How will we explain or demonstrate the activity?

How will we support pupils who are unsure or need extra help?

## Our shared opening and/or finale ideas

Opening idea: how will the class welcome the audience?

Finale idea: how will everyone finish together?

What will our team contribute to the shared section?

## Success check

|  | Check |
| --- | --- |
| ☐ | The audience has an active part. |
| ☐ | Instructions will be simple. |
| ☐ | The activity can be completed safely in the time. |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Roles and responsibilities

Agree a clear role and responsibilities for every team member. Roles may be combined where needed.

Practice model: Possible roles • Workshop Leader • Performer and Demonstrator • Host • Resource Coordinator • Timekeeper / Technical Support

| Team member | Job role | Responsibilities |
| --- | --- | --- |

How did the team make sure the responsibilities were fair and clear?

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# My own role and tasks

## Your task

Agree your role and the specific tasks that you will complete.

## Why are you doing this?

A job title is not enough: the team needs to know exactly what you will do and when you will do it.

## Steps

- Choose a suitable role.

- List your tasks.

- Agree how the team will know each task is complete.

## Evidence to keep

Your role and task list show your individual planning contribution.

| Field | Your information |
| --- | --- |
| My role |  |
| Why this role suits me |  |

| My agreed task | What a finished task will look like | Deadline |
| --- | --- | --- |

Who might I need to work with or support?

What help or approval might I need?

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Key tasks

Break the team idea into clear tasks. Include planning, creating, practising, testing, reviewing and event-day delivery.

Practice model: Rhythm Makers tasks • choose three rhythms • create a short performance • prepare instructions and rhythm cards • practise explanations • test the workshop with classmates • review timing • deliver the workshop

| No. | Key task | Person responsible | How we will check it |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Resources, equipment and safe working

Practice model: Rhythm Makers resources • rhythm cards • timer • speaker • backing track • cue cards • classroom percussion

## Resources and equipment

| Resource or equipment | Why it is needed | Where it will come from | Approval needed? |
| --- | --- | --- | --- |

## Health-and-safety considerations

| Hazard or need | Who could be affected? | Safe action |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Timescales and review dates

Set a completion date for each key stage. Include dates when the team will stop, review progress and update the plan.

| Target / task | Completion date | Team member(s) responsible | Review / status |
| --- | --- | --- | --- |

| Field | Your information |
| --- | --- |
| Review date 1 |  |
| Review date 2 |  |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Performance plan

Performance title and style

What happens at the beginning?

What happens in the middle?

How does the performance finish?

| Performer / technician | What they do | Equipment or cue |
| --- | --- | --- |

How will we practise and test the performance?

Backup plan if a performer or piece of equipment is unavailable

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Workshop step-by-step plan

Plan exactly what the leaders and primary pupils will do. Keep the whole activity within ten minutes.

| Step | Workshop leader does / says | Primary pupils do | Resource |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |

How will we adapt the activity if the group finds it too easy or too difficult?

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Workshop timing and instructions

## Workshop timing plan

| Time | Activity | Lead person | Cue to move on |
| --- | --- | --- | --- |

## Instructions we will give the primary pupils

Welcome and first instruction

The clearest words for explaining the main activity

Safety instruction

How we will praise, encourage and finish

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Weekly task log (1 of 2)

Record what you completed in each lesson. Keep entries brief and specific.

| Date | Task completed | Problem or change | Next step | Teacher initials |
| --- | --- | --- | --- | --- |

Evidence created or saved during these lessons

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Weekly task log (2 of 2)

Record what you completed in each lesson. Keep entries brief and specific.

| Date | Task completed | Problem or change | Next step | Teacher initials |
| --- | --- | --- | --- | --- |

Evidence created or saved during these lessons

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Progress review

Complete this review at the agreed date. Discuss your answers with your team and teacher.

| Field | Your information |
| --- | --- |
| Review date |  |
| Candidate name |  |

What key tasks have been completed?

What resources have been used?

Have roles or responsibilities changed? If so, in what way?

Are timescales being met? If not, why have they changed?

Was anything missing from the plan? How were new tasks allocated?

What needs to happen next?

Teacher review

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Event-day checklist

Use this checklist before the primary pupils arrive and again after the event.

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Everyone knows their role and arrival time. | ☐ | Accessible alternatives are ready. |
| ☐ | Performance and workshop have been rehearsed. | ☐ | Staff approval has been confirmed. |
| ☐ | Instructions and presenter words are ready. | ☐ | The room is welcoming and tidy. |
| ☐ | All resources are prepared and labelled. | ☐ | Emergency exits are clear. |
| ☐ | Instruments and equipment are checked. | ☐ | The team knows the opening and finale cues. |
| ☐ | Sound and playback are tested. | ☐ | A backup plan is ready. |
| ☐ | Cables and walking routes are clear. | ☐ | Afterwards, equipment is returned safely. |
| ☐ | Workshop timing has been tested. | ☐ | Evidence of my contribution is recorded. |

My event-day responsibilities

My backup task if the plan changes

Final message or cue I must remember

Teacher event-day sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# What I contributed

## Your task

Record the work you personally completed during planning, preparation and event delivery.

## Why are you doing this?

This helps you recognise your strengths and prepare for the formal Christmas project.

## Evidence to keep

Your contribution record and any attached or saved work become practice evidence.

Ideas I contributed

Tasks or products I completed

What I did during rehearsals or testing

What I did on the event day

How I supported another team member

Evidence that shows my work (file, photo, script, resource or teacher observation)

Teacher sign-off

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

AUTUMN MUSIC EXPERIENCE | PRACTICE EVIDENCE

# Autumn reflection

Use specific examples. Explain what happened and what you learned.

What worked well in our performance, workshop or team organisation?

What could be improved, and why?

What did I do well?

What should I develop?

What will I apply to the Christmas Community Celebration?

## Success check

|  | Check |
| --- | --- |
| ☐ | I used examples. |
| ☐ | I identified an improvement. |
| ☐ | I explained what I will do differently at Christmas. |

PROJECT 2

Christmas Community Celebration

Qualifications Scotland Assessment Evidence

This is your formal Creative Project. Your planning, practical work, progress reviews and evaluation provide evidence for J17Y 75.

PROJECT 2 | FORMAL ASSESSMENT

# Christmas Community Celebration brief

## Client

King’s Park Events Company — A fictional creative events company based within King’s Park Secondary School.

## Target audience

A mixed group of approximately 20–30 invited community guests. The group may include:

- local care-home residents;

- members of community groups;

- older relatives;

- other invited guests.

## Background

King’s Park Events Company has been asked to create a welcoming Christmas community event. The aim is to bring people together through Christmas music, creative activities, refreshments, conversation and positive interaction between pupils and guests.

## Requirements

|  | Check |
| --- | --- |
| ☐ | The event takes place during the school day. |
| ☐ | It lasts approximately 60 minutes. |
| ☐ | It takes place in the assembly hall. |
| ☐ | It uses a mixture of performance seating and social tables. |
| ☐ | It is delivered at the end of Term 2. |
| ☐ | Planning begins immediately after the October holiday. |
| ☐ | Pupils decide the final event format. |

Different ways to contribute Not every team must perform. Teams may focus on hospitality, activities, technical production, invitations, design, front of house, accessibility or organisation.

PROJECT 2 | FORMAL ASSESSMENT

# Christmas brief: possibilities and constraints

## The event may include

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Christmas performances | ☐ | hot or cold drinks |
| ☐ | singalongs | ☐ | decorations |
| ☐ | bingo | ☐ | presenters |
| ☐ | quizzes | ☐ | prizes |
| ☐ | games | ☐ | cards or small gifts |
| ☐ | cakes and biscuits | ☐ | social time |

Performers may come from the Creative Industries class, the wider Music Department, other school departments or other pupil groups.

## Considerations and constraints

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Use existing school resources; there is no fixed budget. | ☐ | The programme should be Christmas themed. |
| ☐ | Any spending or prizes require staff approval. | ☐ | Liaison with Home Economics may support cakes, biscuits and drinks. |
| ☐ | Pupils create invitations; staff approve and manage external communication. | ☐ | Music, Drama, Dance/PE, Music Technology, Art and Design or other departments may help. |
| ☐ | Care homes or community organisations arrange guest transport. | ☐ | Event-day dress is Christmas jumpers unless staff confirm otherwise. |

## Accessibility and safe guest care

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | food allergies and dietary requirements | ☐ | safe movement, cables and equipment |
| ☐ | wheelchair access and mobility | ☐ | arrival, departure and emergency exits |
| ☐ | hearing and sight needs | ☐ | safe food service |
| ☐ | accessible toilets and seating comfort |  |  |

## Client expectations

Guests should feel welcomed and included, enjoy the music, activities and refreshments, have opportunities to speak with pupils and leave with a positive view of King’s Park.

Overall standard The project must be creative and original, enjoyable, safe, realistic, completed within the agreed timescale and organised so that everyone contributes.

PROJECT 2 | SUGGESTIONS

# Christmas ideas bank: programme

Class choice These ideas are suggestions. The class decides the final event.

| Performance ideas • Christmas choir • solo vocal performance • instrumental solo • small ensemble • school band • acoustic group • Christmas medley • carol performance • audience singalong • familiar Christmas songs • Christmas music from different cultures • musical theatre performance • dance performance • drama scene • festive sketch • Christmas poem • spoken-word performance • Christmas story • pupil-hosted variety show • guest performer • teacher performance • recorded music between activities | Audience activity ideas • Christmas bingo • music bingo • Christmas quiz • picture quiz • guess the Christmas song • name that tune • finish the lyric • Christmas trivia • festive word game • table quiz • pass-the-parcel-style activity • raffle • prize draw • audience percussion • singalong • request-a-song section • memory game • Christmas reminiscence prompts • decorate a card • simple craft activity • conversation cards • table games • musical game show |
| --- | --- |

PROJECT 2 | SUGGESTIONS

# Christmas ideas bank: guest experience and production

| Hospitality ideas • tea • coffee • hot chocolate • cold drinks • biscuits • cakes • mince pies • Christmas baking • small afternoon-tea selection • festive napkins • table service • refreshment station • printed menu • allergen labels • dietary-option labels | Guest-experience ideas • printed or personalised invitations • welcome signs and front-of-house team • coat area • table plan and reserved accessible seating • event programme and name badges • Christmas decorations and table centrepieces • background music • welcome speech and presenters • guided arrival and social time • pupil conversation hosts • cards or small handmade gifts • memory wall • Christmas photo area, subject to permission • thank-you message • safe departure plan |
| --- | --- |

## Production ideas

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | running order | ☐ | equipment list |
| ☐ | presenter script | ☐ | signage |
| ☐ | microphone plan | ☐ | rehearsal schedule |
| ☐ | playback plan | ☐ | performer briefing |
| ☐ | sound check | ☐ | event-day staffing plan |
| ☐ | lighting plan | ☐ | contingency plan |
| ☐ | room layout | ☐ | health-and-safety checklist |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Project outputs tracker (1 of 2)

The class decides which products are needed. Each team must create finished evidence linked to its responsibilities. Mark each product as required or not required, then record ownership and progress.

| Possible product | Required? | Team / owner | Deadline | Status | Evidence location |
| --- | --- | --- | --- | --- | --- |
| Invitations |  |  |  |  |  |
| Guest list |  |  |  |  |  |
| Event programme |  |  |  |  |  |
| Performance running order |  |  |  |  |  |
| Bingo materials |  |  |  |  |  |
| Quiz materials |  |  |  |  |  |
| Food and hospitality plan |  |  |  |  |  |
| Allergen and dietary-information plan |  |  |  |  |  |
| Room layout |  |  |  |  |  |
| Seating plan |  |  |  |  |  |
| Decoration plan |  |  |  |  |  |

Products our team is responsible for

Where finished files or physical evidence will be kept

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Project outputs tracker (2 of 2)

The class decides which products are needed. Each team must create finished evidence linked to its responsibilities. Mark each product as required or not required, then record ownership and progress.

| Possible product | Required? | Team / owner | Deadline | Status | Evidence location |
| --- | --- | --- | --- | --- | --- |
| Technical plan |  |  |  |  |  |
| Microphone and sound plan |  |  |  |  |  |
| Presenter scripts |  |  |  |  |  |
| Signs |  |  |  |  |  |
| Event-day staffing schedule |  |  |  |  |  |
| Rehearsal schedule |  |  |  |  |  |
| Health-and-safety checklist |  |  |  |  |  |
| Accessibility checklist |  |  |  |  |  |
| Contingency plan |  |  |  |  |  |
| Event-day checklist |  |  |  |  |  |

Products our team is responsible for

Where finished files or physical evidence will be kept

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Chosen-product planning sheet (1 of 2)

Use this page for a major product your team must finish. Add another copy if required.

## Product 1

| Field | Your information |
| --- | --- |
| Product name |  |
| Owner(s) |  |
| Deadline |  |

Purpose and audience

What the finished product must include

Resources, approval or support needed

Steps to complete the product

Quality check before it is final

Where the finished evidence will be stored

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Chosen-product planning sheet (2 of 2)

Use this page for a major product your team must finish. Add another copy if required.

## Product 2

| Field | Your information |
| --- | --- |
| Product name |  |
| Owner(s) |  |
| Deadline |  |

Purpose and audience

What the finished product must include

Resources, approval or support needed

Steps to complete the product

Quality check before it is final

Where the finished evidence will be stored

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Outcome 1 — Plan the project

What this outcome means I contribute ideas, identify tasks and resources, agree responsibilities and help set deadlines.

## Your task

Work with your class and team to produce an agreed plan for a suitable, manageable Christmas community event.

## Why are you doing this?

The group plan is required formal evidence. Your teacher must approve the plan before implementation begins.

## Steps

- Understand the brief and audience.

- Contribute ideas during planning discussion.

- Agree tasks, resources, roles and responsibilities.

- Agree your own tasks, deadlines and at least two review dates.

- Check health and safety, accessibility and staff approval.

## Evidence to keep

Keep the completed group plan, role allocation, timescales and teacher approval in this booklet.

## Understanding the brief

What is the client asking the class to create?

Which requirements cannot be changed?

Which decisions can the pupils make?

## Audience needs

What will help community guests feel welcomed, included, safe and comfortable?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Ideas and planning discussion

## My individual ideas

My idea for the event format or programme

My idea for helping guests participate or feel welcome

My idea for a product, resource or practical solution

Why one of my ideas suits the brief and audience

## Ideas shared during the planning discussion

| Idea shared | Who contributed it? | Benefit or concern | Used in final plan? |
| --- | --- | --- | --- |

How did the group reach a fair decision?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Final agreed team response

| Field | Your information |
| --- | --- |
| Group project title |  |
| Team name |  |
| Team members |  |

Describe the final agreed team response

What will our team create or deliver?

How will our work contribute to the full class event?

How does our response meet the client brief?

How will our response meet the needs of community guests?

## Success check

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Suitable and manageable | ☐ | Safe and accessible |
| ☐ | Creative and original | ☐ | Clear contribution from every member |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Official group plan

Editable adaptation of the official J17Y 75 group-plan form. A completed copy is required evidence.

| Field | Your information |
| --- | --- |
| Candidate’s name |  |
| Class |  |

## Group members

| Name | Name | Name |
| --- | --- | --- |

Project idea / title

Key tasks

Resources

Assessor check

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Key tasks required to implement the project

List the major tasks needed to move from the agreed idea to a finished event. Include planning, creating, rehearsing, testing and delivery.

| No. | Key task | Finished result | Dependencies / approval | Owner |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| 8 |  |  |  |  |
| 9 |  |  |  |  |
| 10 |  |  |  |  |

Tasks that must be completed by the whole class rather than one team

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Resources required to implement the project

Resources include skills and people as well as physical items. Be specific about what is needed and why.

| Resource category | Specific resource | Purpose | Source / person | Approval or safety check |
| --- | --- | --- | --- | --- |
| Practical skills |  |  |  |  |
| Techniques |  |  |  |  |
| Equipment |  |  |  |  |
| Materials |  |  |  |  |
| People |  |  |  |  |
| Spaces |  |  |  |  |
| Time |  |  |  |  |
| Information |  |  |  |  |

Resource that could be difficult to obtain

Alternative resource or contingency

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Roles and responsibilities

For each key task, allocate roles and responsibilities. Every candidate needs a clear individual contribution.

| Group member name | Group member job role | Responsibilities |
| --- | --- | --- |

How did I contribute to allocating roles and responsibilities?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# My role and agreed individual tasks

| Field | Your information |
| --- | --- |
| My role |  |
| My main responsibility |  |
| Why this role is suitable |  |

| My agreed task | Expected result | Deadline | Who I will work with | Evidence |
| --- | --- | --- | --- | --- |

How will I know that my tasks have been completed to a good standard?

What support, training or approval will I need?

How might I support another team member?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Timescales for key stages (1 of 2)

Editable adaptation of the official timescales form. Include interim deadlines and review dates.

| Target / task | Completion date | Name of group member(s) responsible for task completion |
| --- | --- | --- |

Any fixed dates or dependencies that affect this plan

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Timescales for key stages (2 of 2)

| Target / task | Completion date | Name of group member(s) responsible for task completion |
| --- | --- | --- |

## Agreed review dates

| Field | Your information |
| --- | --- |
| Review date 1 |  |
| Review date 2 |  |
| Additional review date |  |

Assessor’s comments

| Assessor’s signature | Date |
| --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Health-and-safety and accessibility plan

Plan controls before implementation. Include guests, pupils, staff and anyone setting up or clearing the hall.

| Hazard or accessibility need | Who could be affected? | Control / reasonable adjustment | Responsible person | Checked |
| --- | --- | --- | --- | --- |

## Required areas

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Allergens and dietary needs checked | ☐ | Seating and movement routes checked |
| ☐ | Wheelchair and mobility access checked | ☐ | Cables, equipment and exits checked |
| ☐ | Hearing and sight needs considered | ☐ | Safe food service planned |
| ☐ | Accessible toilets confirmed | ☐ | Arrival and departure planned |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Collaboration and approval before implementation

## Collaboration with other departments

| Department / person | What support is requested? | Who will liaise? | Staff approval / date | Outcome |
| --- | --- | --- | --- | --- |

Communication rule External communication with invited guests, care homes and community organisations must be handled or approved by staff.

## Teacher approval before implementation

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | The project is suitable and manageable. | ☐ | Timescales and at least two review dates are agreed. |
| ☐ | Key tasks and resources are clear. | ☐ | Health, safety and accessibility controls are suitable. |
| ☐ | Roles, responsibilities and individual tasks are agreed. | ☐ | Any spending, equipment use and external contact are approved. |

Conditions or changes required before the team begins

| Approved to begin? | Teacher name | Signature | Date |
| --- | --- | --- | --- |
| Yes / Not yet |  |  |  |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Outcome 2 — Deliver the project

What this outcome means I complete my agreed tasks, use resources safely, review progress and support my team.

## Your task

Put the approved plan into action in a real or simulated working environment under supervision.

## Why are you doing this?

Your practical work and teacher observations show whether you can contribute effectively and work safely.

## Steps

- Carry out your agreed tasks as planned.

- Use practical skills, resources, techniques and equipment as planned.

- Follow relevant health-and-safety guidelines.

- Review progress at the agreed dates and update the plan.

- Support other team members while undertaking activity.

## Evidence to keep

Keep task logs, products, practical-work records, reviews and teacher observations.

## Before you begin

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | The teacher has approved the plan. | ☐ | I know the relevant safety controls. |
| ☐ | I know my role and tasks. | ☐ | I know where evidence will be stored. |
| ☐ | I know the deadlines and review dates. | ☐ | I know who I may need to support. |

My first priority

The first person I need to work with

The first resource or approval I need

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Weekly task log (1 of 2)

Record your own work after each practical session. State what changed and what you will do next.

| Date | Task completed | Problem or change | Next step | Teacher initials |
| --- | --- | --- | --- | --- |

Evidence produced or updated during these lessons

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Weekly task log (2 of 2)

Record your own work after each practical session. State what changed and what you will do next.

| Date | Task completed | Problem or change | Next step | Teacher initials |
| --- | --- | --- | --- | --- |

Evidence produced or updated during these lessons

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Practical work record

Use this record for significant practical activities. Attach or identify any finished evidence created.

| Date | Practical activity | My contribution | Skills / techniques / equipment | Result or evidence | Teacher initials |
| --- | --- | --- | --- | --- | --- |

Best example of my practical work and why it is strong

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Progress Review 1

Complete this review at the agreed date. Discuss progress with your group and teacher where appropriate.

| Candidate’s name |  | Class |  | Agreed review date |  |
| --- | --- | --- | --- | --- | --- |

What key tasks have been completed?

What resources have been used?

Have roles or responsibilities changed?

Are timescales being met?

Was anything missing from the plan?

How were new tasks allocated?

What needs to happen next?

Assessor’s comments

| Assessor’s signature | Date |
| --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Progress Review 2

Complete this review at the agreed date. Discuss progress with your group and teacher where appropriate.

| Candidate’s name |  | Class |  | Agreed review date |  |
| --- | --- | --- | --- | --- | --- |

What key tasks have been completed?

What resources have been used?

Have roles or responsibilities changed?

Are timescales being met?

Was anything missing from the plan?

How were new tasks allocated?

What needs to happen next?

Assessor’s comments

| Assessor’s signature | Date |
| --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Changes to the plan and resources used

## Changes made to the plan

| Original plan | Change made | Reason | Who agreed it? | Effect on deadline / quality |
| --- | --- | --- | --- | --- |

## Resources used

| Resource | How it was used | Effective? | Change or alternative |
| --- | --- | --- | --- |

Resource we should have planned differently

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Skills, safe working, support and evidence

## Skills and techniques used

| Skill or technique | How I used it | Result |
| --- | --- | --- |

Health-and-safety actions I took

How I supported other team members

Evidence I produced or helped produce

Where the evidence is saved or attached

## Success check

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | I used resources appropriately. | ☐ | I reported problems early. |
| ☐ | I followed staff instructions. | ☐ | I helped someone when appropriate. |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Event-day responsibilities and running order

## My event-day responsibilities

| Time / stage | My responsibility | Who I work with | Equipment / information | Backup action |
| --- | --- | --- | --- | --- |

## Event running order

| Time | Item / activity | Lead | Technical / room cue |
| --- | --- | --- | --- |

Who makes the final decision if the running order must change?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Final preparation checklist

Complete this with your team before the event day.

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Invitations and guest information are approved. | ☐ | Accessible seating and routes are ready. |
| ☐ | Guest numbers and accessibility needs are confirmed by staff. | ☐ | Decorations and signs are prepared. |
| ☐ | Programme and running order are final. | ☐ | Microphones, sound and playback are tested. |
| ☐ | Presenters, performers and activity leaders are briefed. | ☐ | Equipment is labelled and stored safely. |
| ☐ | Rehearsals are complete. | ☐ | Staffing schedule is clear. |
| ☐ | Scripts, games, quizzes or bingo materials are final. | ☐ | Contingency plans are understood. |
| ☐ | Hospitality plan is approved. | ☐ | Arrival and departure plans are confirmed. |
| ☐ | Allergens and dietary information are clear. | ☐ | Emergency exits will remain clear. |
| ☐ | Room layout and seating plan are approved. | ☐ | Photography or recording permission is confirmed. |

Outstanding task

Person responsible

Final deadline

Teacher action or approval needed

Teacher readiness check

| Teacher initials | Date | Brief comment |
| --- | --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Event-day checklist

## Before guests arrive

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Room, tables and seating are safely arranged. | ☐ | Sound, microphones, playback and lighting are tested. |
| ☐ | Accessible routes, toilets and reserved seating are clear. | ☐ | Signs, programmes and activity materials are in place. |
| ☐ | Front-of-house, hospitality and technical teams are ready. | ☐ | Presenters and performers know their cues. |
| ☐ | Food, drink and allergen information are checked. | ☐ | Emergency exits and cables are safe. |

## During the event

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Guests are welcomed and supported. | ☐ | Safety and accessibility are monitored. |
| ☐ | The running order and timings are monitored. | ☐ | Changes are communicated calmly. |
| ☐ | Pupils speak and behave appropriately with guests. | ☐ | Team members support each other. |

## After the event

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | Guests leave safely. | ☐ | The hall is left tidy. |
| ☐ | Equipment is switched off and returned. | ☐ | Finished evidence is collected and saved. |
| ☐ | Food and waste are cleared safely. | ☐ | Problems or incidents are reported to staff. |

My key responsibility today

Change or issue I dealt with

Evidence of my event-day contribution

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Teacher observation record

This page records observed practical contribution during implementation. The formal criteria checklists are in the Teacher Assessment Pages at the back.

| Field | Your information |
| --- | --- |
| Candidate’s name |  |
| Class |  |
| Observation date(s) |  |

| Observed area | Evidence / comment | Date | Teacher initials |
| --- | --- | --- | --- |
| Carried out own tasks |  |  |  |
| Used skills, resources, techniques and equipment |  |  |  |
| Worked safely |  |  |  |
| Reviewed progress |  |  |  |
| Supported others |  |  |  |
| Event-day contribution |  |  |  |

Overall observation comment

| Teacher name | Signature | Date |
| --- | --- | --- |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Outcome 3 — Evaluate the project

What this outcome means I explain what worked, what could improve and what should be done differently next time.

## Your task

Evaluate your own contribution, your team’s contribution and the implementation of the project. Then identify at least two future action points.

## Why are you doing this?

A strong evaluation uses specific evidence. It explains why something was effective or ineffective, rather than only saying that it was good or bad.

## Steps

- Use examples from planning, preparation and event delivery.

- Identify strengths and areas for development.

- Judge the plan, resources, techniques, equipment, safety and audience experience.

- Write at least two specific actions for future creative projects.

## Evidence to keep

Your completed evaluation is formal Outcome 3 evidence and must be your own work.

## Evaluation coverage

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | My contribution | ☐ | Strengths |
| ☐ | Team contribution | ☐ | Areas for development |
| ☐ | Project implementation | ☐ | At least two action points |

Evidence or examples I will use in my evaluation

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Evaluation: my contribution

Ideas I contributed during planning

Agreed tasks I completed

How I used skills, resources, techniques or equipment

How I worked safely

How I supported other team members

Strengths in my contribution — include specific examples

Areas for development in my contribution — explain why

## Success check

|  | Check |
| --- | --- |
| ☐ | I evaluated rather than only described. |
| ☐ | I used evidence. |
| ☐ | I identified a realistic improvement. |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Evaluation: team contribution

How well did the team share ideas and make decisions?

How well did the team allocate and complete responsibilities?

How well did team members communicate and meet deadlines?

How did the team respond to problems or changes?

How did team members support each other?

Strengths of the team — include specific examples

Areas for development for the team — explain why

## Success check

|  | Check |
| --- | --- |
| ☐ | I considered the whole team. |
| ☐ | I used examples. |
| ☐ | I explained how teamwork affected the project. |

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Evaluation: project implementation (1 of 2)

What worked well during preparation and event delivery? Why?

What did not work as planned? Why?

How effective were the resources, techniques and equipment?

How useful was the original plan in structuring the work?

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Evaluation: project implementation (2 of 2)

How well were health, safety and accessibility managed?

Did the project meet the client brief? Give evidence.

Was the audience experience successful? Explain using observed evidence.

Overall strength of the implementation

Main area for development in the implementation

CHRISTMAS COMMUNITY CELEBRATION | QUALIFICATIONS SCOTLAND ASSESSMENT EVIDENCE

# Future action points and final evaluation check

Identify at least two specific actions that would improve the planning and implementation of future creative projects.

| Action point | What I or the team would do | Why this would improve a future project | When / how it would happen |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| Optional 3 |  |  |  |

## Final evaluation check

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | I evaluated my own contribution. | ☐ | I identified areas for development. |
| ☐ | I evaluated the team contribution. | ☐ | I gave at least two future action points. |
| ☐ | I evaluated implementation. | ☐ | I used specific examples. |
| ☐ | I identified strengths. | ☐ | This is my own work. |

Assessor’s comments

| Assessor’s signature | Date |
| --- | --- |

FINAL PUPIL SELF-CHECK

# Have I completed my evidence?

## Outcome 1 — Plan

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | I helped agree the project. | ☐ | I helped allocate roles. |
| ☐ | I helped identify tasks. | ☐ | I agreed my own tasks. |
| ☐ | I helped identify resources. | ☐ | I helped set deadlines and review dates. |

## Outcome 2 — Deliver

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | I completed my tasks. | ☐ | I reviewed progress. |
| ☐ | I used resources and equipment appropriately. | ☐ | I supported others. |
| ☐ | I worked safely. |  |  |

## Outcome 3 — Evaluate

|  | Check |  | Check |
| --- | --- | --- | --- |
| ☐ | I evaluated my contribution. | ☐ | I identified strengths. |
| ☐ | I evaluated the team. | ☐ | I identified areas for improvement. |
| ☐ | I evaluated the event. | ☐ | I wrote at least two action points. |

Evidence that still needs to be completed or attached

Action I will take before final submission

| Pupil signature | Date | Teacher initials |
| --- | --- | --- |

ADDITIONAL BOOKLET RECORD

# Absence and catch-up record

Use this page to make a clear plan for catching up after absence.

| Date absent | Work missed | Catch-up action | Completed | Teacher initials |
| --- | --- | --- | --- | --- |

Current catch-up priority

Support I need

ADDITIONAL BOOKLET RECORD

# Teacher feedback and pupil response (1–2)

## Feedback cycle 1

Teacher feedback

What I need to improve

My response / action

| Review date | Teacher initials | Progress at review |
| --- | --- | --- |

## Feedback cycle 2

Teacher feedback

What I need to improve

My response / action

| Review date | Teacher initials | Progress at review |
| --- | --- | --- |

ADDITIONAL BOOKLET RECORD

# Teacher feedback and pupil response (3–4)

## Feedback cycle 3

Teacher feedback

What I need to improve

My response / action

| Review date | Teacher initials | Progress at review |
| --- | --- | --- |

## Feedback cycle 4

Teacher feedback

What I need to improve

My response / action

| Review date | Teacher initials | Progress at review |
| --- | --- | --- |

ADDITIONAL BOOKLET RECORD

# Notes (1 of 2)

Use this page for meeting notes, reminders, sketches or evidence references.

ADDITIONAL BOOKLET RECORD

# Notes (2 of 2)

Use this page for meeting notes, reminders, sketches or evidence references.

Teacher Assessment Pages

J17Y 75 — Formal assessment record

Use these pages to record the candidate’s achievement against the exact formal outcomes and performance criteria.

TEACHER ASSESSMENT PAGES

# Formal outcomes and evidence requirements

Outcome 1 Contribute to the production of a plan for a creative project in response to a given brief.

Outcome 2 Contribute to the implementation of a creative project.

Outcome 3 Evaluate the creative project.

## Required evidence

|  | Check |
| --- | --- |
| ☐ | Performance evidence and written and/or oral evidence cover all Outcomes and Performance Criteria. |
| ☐ | Written evidence is gathered in a candidate folio under open-book conditions. |
| ☐ | Outcome 1 includes supervised performance evidence, an assessor observation checklist and a copy of a group plan. |
| ☐ | Outcome 2 practical activities are supervised in a real or simulated working environment and supported by an assessor observation checklist. |
| ☐ | Practical activities are carried out safely and relevant health-and-safety guidelines are followed. |
| ☐ | Outcome 3 evidence is the candidate’s own work and includes evaluation plus at least two future action points. |

Local evidence design The booklet requires two agreed progress-review dates. The formal NAB wording requires review dates but does not specify a minimum number. The two-review requirement is a local strengthening of the evidence plan.

TEACHER ASSESSMENT PAGES

# Outcome 1 observation checklist

Formal Outcome 1: Contribute to the production of a plan for a creative project in response to a given brief.

| Field | Your information |
| --- | --- |
| Candidate’s name |  |
| Class |  |

| Criterion | Performance criterion | Achieved / not yet | Date | Evidence / comment |
| --- | --- | --- | --- | --- |
| (a) | Agree a suitable creative project. |  |  |  |
| (b) | Identify key tasks required to implement the creative project. |  |  |  |
| (c) | Identify resources required to implement the creative project. |  |  |  |
| (d) | Contribute to the allocation of roles and responsibilities. |  |  |  |
| (e) | Agree own tasks required to implement the creative project. |  |  |  |
| (f) | Agree timescales and review dates for the creative project. |  |  |  |

Assessor’s comments

| Assessor’s name | Assessor’s signature | Date |
| --- | --- | --- |

TEACHER ASSESSMENT PAGES

# Outcome 2 observation checklist

Formal Outcome 2: Contribute to the implementation of a creative project.

| Field | Your information |
| --- | --- |
| Candidate’s name |  |
| Class |  |

| Criterion | Performance criterion | Achieved / not yet | Date | Evidence / comment |
| --- | --- | --- | --- | --- |
| (a) | Carry out own tasks as planned. |  |  |  |
| (b) | Use practical skills, resources, techniques and equipment as planned. |  |  |  |
| (c) | Comply with relevant health and safety guidelines. |  |  |  |
| (d) | Review progress of the creative project at agreed dates. |  |  |  |
| (e) | Support others while undertaking activity. |  |  |  |

Assessor’s comments

| Assessor’s name | Assessor’s signature | Date |
| --- | --- | --- |

TEACHER ASSESSMENT PAGES

# Outcome 3 assessment checklist

Formal Outcome 3: Evaluate the creative project.

## Exact formal performance criteria

| Criterion | Performance criterion |
| --- | --- |
| (a) | Evaluate own and team contribution to the creative project. |
| (b) | Evaluate implementation of the creative project. |

| Field | Your information |
| --- | --- |
| Candidate’s name |  |
| Class |  |

## Evidence indicators

| Evidence indicator | Achieved / not yet | Date | Evidence / comment |
| --- | --- | --- | --- |
| Evaluates own contribution |  |  |  |
| Evaluates team contribution |  |  |  |
| Evaluates implementation |  |  |  |
| Identifies strengths |  |  |  |
| Identifies areas for development |  |  |  |
| Gives at least two future action points |  |  |  |

Assessor’s comments

| Assessor’s name | Assessor’s signature | Date |
| --- | --- | --- |

TEACHER ASSESSMENT PAGES

# Candidate Unit assessment record

Skills for Work: Creative Industries

Creative Industries: Creative Project (National 5)

| Class |  | Group |  |
| --- | --- | --- | --- |
| Candidate’s name |  | Candidate’s ID |  |

## Record of performance

| Outcome | Formal outcome | Achieved / not achieved | Comments |
| --- | --- | --- | --- |
| 1 | Contribute to the production of a plan for a creative project in response to a given brief. |  |  |
| 2 | Contribute to the implementation of a creative project. |  |  |
| 3 | Evaluate the creative project. |  |  |

Enter A or NA to indicate whether the candidate has achieved or not achieved each Outcome. Use the comments column to identify evidence or any re-assessment needed.

Overall comments

| Assessor’s name | Assessor’s signature | Date |
| --- | --- | --- |